## Project Planner
Solitaire Project Plan
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | NUMBER OF DAYS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
| Texture Pack | 1 | 3 | NA | NA | 0%
| Card Class (parent class) | 4 | 9 | NA | NA | 0%
| Cardpile Class | 9 | 15 | NA | NA | 0%
| Suit Pile | 15 | 19 | NA | NA | 0%
| Discard Pile | 15 | 19 | NA | NA | 0%
| Deck Pile | 19 | 23 | NA | NA | 0%
| Table Pile | 19 | 23 | NA | NA | 0%
| Solitaire Game Class | 23 | 28 | NA | NA | 0%
| Solitaire Frame (GUI) | 23 | 28 | NA | NA | 0%
Kelly TEXTURES CARPET (Start Date: 3/21/22) - (Due: 3/23/22) -Get all the images for the cards and backgrounds. Could also include textures for the buttons.
Brook Card Class (Start Date: 3/24/22) - (Due: 3/29/22) -The dimensions of the card, how it looks both on the front and the back. -Suit (clubs, diamonds, spades or hearts) and Rank (K, Q, J, 10, etc.)
Brook Cardpile Class (Start Date: 3/29/22) - (Due: 4/4/22) -Virtual representation of the full deck of 64 cards.
Ana SuitPile [1] (Start Date: 4/4/22) - (Due: 4/8/22) -4 piles for the pile of suits -Takes their respective cards and denies any other type of card (incorrect suit or incorrect rank)
Zamzam Discard Pile [2] (Start Date: 4/4/22) - (Due: 4/8/22) -Cards are face up on the discard pile. [Preview with face-up cards.]
Zamzam Deck pile Class [3] (Start Date: 4/8/22) - (Due: 4/12/22) -Shuffles cards. -Cards are face down.
Ana TablePile [4] (Start Date: 4/8/22) - (Due: 4/12/22) - 7 decks of cards to construct.
Kelly Solitaire Game Class (Start Date: 4/12/22) - (Due: 4/17/22) -Creates an instance of the game. -Creates a window, initializes the game and displays it.
Ana Solitaire Frame (Start Date: 4/12/22) - (Due: 4/17/22) - GUI Window - Has listeners for clicks - Deals with the user interaction with buttons and cards. -Takes care of the game itself and the gameplay.